| NATURAL RESOURCES | CLRP: Priority | CLRP: Lead Board(s) | INFO FROM BOARD: Current Status |
| --- | --- | --- | --- |
| Goal NR-1. Preserve Lincoln`s natural resources and agricultural land uses. |  |  |  |
| RECOMMENDATIONS ACTION STEPS: |  |  |  |
| NR-1.1.By purchase, restriction, or other method, continue to protect lands which contain or contribute to the protection of valuable natural resources, including public drinking water supplies. | Ongoing | CC | CC: High priority; coop needed from RLF, LLCT, SuAsCo CISMA Cambridge; See Conservation Projects in OS - 1.4 ; Deed Restrictions through wetland permitting |
| NR-1.1.1. Maintain close working relationships between the Conservation Commission, Lincoln Land Conservation Trust, Rural Land Foundation, and others to protect conservation and watershed land. |  |  | CC: The CC keeps a close working relationship with the RLF and LLCT and other regional governmental agencies and non-profit organizations. |
| NR-1.1.2. Continue to implement the 2008 Open Space and Recreation Plan. |  |  | CC continues to evaluate the OSRP and take on its described action items. |
| NR-1.2. Continue to secure deed restrictions to protect wetland buffer zone areas. | Ongoing | CC | CC: During wetlands permitting the CC does work with landowners to place deed restrictions protecting buffer zone and wetlands when appropriate. This is typically when a property with development constraints is being built on or having an existing use expanded. We want to be sure that there is no incremental creep over time into protected areas. |
| NR-1.2.1. Maintain the town’s practice of securing conservation restrictions as part of the wetlands permitting process, especially for expansion of existing properties. |  |  | CC: We have used “deed restrictions” rather than CRs for protecting certain parcels during the wetlands permitting process. These are much easier to execute and serve to keep future owners on notice about the restrictions. |
| NR-1.2.2. Ensure that all conservation restrictions are properly recorded at the Registry of Deeds and entered into the town’s index of land restrictions. |  |  | CC: These wetlands-related Deed Restrictions are recorded at the Registry of Deeds and entered into our conservation database. |
| NR-1.3.Establish policies and regulations for water use – both voluntary and mandatory – in order to conserve water and bring Lincoln in line with the state’s water use guidelines. | Ongoing | WC, CC | CC: The primary authority for water use regulations is the WC and the CC supports them in all such efforts. During wetlands permitting we encourage applicants to employ landscaping methods that minimize the need for future water use. WC: Medium priority. WC is currently enforcing MADEP imposed conservation requirements. Goals won’t be met this year |
| NR-1.3.1. Continue to review the user fee structure and explore other incentives to reduce residential water consumption. | High | WC, BOS | WC: Adopted low water use appliance program; researching bylaw requiring low water use appliances in all new construction BOS: Would like clarification as to BOS authority and role. This would appear to be an action that falls squarely within the Water Board’s jurisdiction. We do not have any special expertise or operational oversight that would be of assistance to the effort. |
| NR-1.3.2. Wherever possible, promote more compact development that consumes less water by design. (See also, NR-4.2, LU-1.1) |  | PB | PB: Ongoing as applicable through Land Use Group staff review and permitting criteria. The PB is sponsoring an Aquifer Protection and Watershed Overlay District that will subject water intensive uses to special permit review |
| NR-1.3.3. As part of Site Plan Review, adopt landscaping guidelines that promote or require drought-resistant plantings and reduce turf cover for all types of development, including single-family dwellings. |  |  | CC: Our Conservation Planner is working on an “Ecological Design and Construction Handbook” that will be a guide to current best management practices (BMPs). Much of this is geared towards minimizing water use and protecting water quality. |
| NR-1.4.Develop property management plans for the protection of conservation land and habitat areas. (See also, OS -2.1) | Ongoing | CC | CC: CC practices sound ecological management but has not prepared parcel-specific plans. This is a low-priority item. |
| NR-1.4.1. Fund the Conservation Commission’s baseline inventory and stewardship programs at a level sufficient to prepare and implement property management plans. |  |  | CC: At this time any funding for management plans will come from the CC operating budget. Should plan development become a high priority then we will pursue funding. |
| NR-1.5.Encourage or require best management practices for soil and water conservation on all construction projects in Lincoln, including agricultural lands to the extent allowed by law. | Ongoing | WC, CC | CC: The Ecological Design and Construction Handbook and the revised Farm Policy will address this need for outreach and education. When the new NPDES MS4 permit is issued by EPA, the Town may need to memorialize this information in a formal bylaw. |
| NR-1.5.1. Study options for a land clearing and grading bylaw in conjunction with work on NR-3.2. |  |  | CC: Under the NPDES guidelines we should be considering such a bylaw in conjunction with the PB. |
| NR-1.5.2. Evaluate preferred option(s) against the town’s existing regulations for subdivision control, site plan approval, and wetlands permits, as well as the state’s most recent version of the Stormwater Management Handbook. |  |  | CC works with the existing state and local wetlands regulations and state stormwater regulations to have builders use current BMPs. |
| NR-1.5.3. Develop a comprehensive approach that avoids conflicts between regulations and consolidates permitting to the maximum extent possible. |  |  |  |
| NR-1.5.4. Propose a land clearing and grading or comparable best management practices bylaw for adoption by Town Meeting. |  |  | See NR-1.5.1. |
| NR-1.6.Ensure that developers comply with requirements for environmental impact reports, stormwater management, and open space development guidelines. | Ongoing | PB | PB: Ongoing as applicable through Land Use Group staff review and permitting criteria |
| NR-1.6.1. Prepare and adopt an environmental “checklist” for use by all town boards with development review responsibilities. |  |  |  |
| NR-1.6.2. Hold periodic joint boards meetings to consult about development projects under review and ensure a consistent approach to permitting. |  |  | Ongoing: PB, ZBA and CC meet in scoping sessions to review and discuss permitting responsibilties are consistent and not redundant. Land Use Chairs Quarterly also reviews projects requiring multple board review to make sure a process for coordination is established. |
| Goal NR-2. Promote water conservation, ecological landscaping practices, and energy and resource conservation among all property owners and town employees. |  |  |  |
| RECOMMENDATIONS ACTION STEPS: |  |  |  |
| NR-2.1.Develop conservation guidelines for all public buildings, including schools, the town offices, public safety, and public works. | High | WC , BOS, WD, FM | BOS: The Town is actively managing its water consumption, particularly the Town Office project, which is pursuing LEED certification. The newer town buildings all have low-flow toilets. The town currently takes a very minimalist approach to landscaping and therefore requires only minimal water for outdoor use. Would be happy to participate in discussion group should the Water Department convene such a group. WC: Low priority. Goals won’t be met this year |
| NR-2.1.1. Work with the Water Department to measure trends in water consumption in municipal and school buildings and to establish performance standards for each type of building, based on its use and occupancy characteristics. |  |  |  |
| NR-2.1.2. Continue to monitor public buildings for energy use and provide conservation training and technical assistance to town and school employees. |  |  |  |
| NR-2.1.3. Equip municipal and school buildings with appropriate conservation fi xtures and properly maintain them. |  |  |  |
| NR-2.2.Continue to educate the public about Lincoln’s conservation ethic and commitment to stewardship. | High | WC , BOS | WC: Medium priority, with significant focus this year BOS: Conservation education is a component of LEED certification for the renovated Town Office building. In addition, BOS has provided seed money to support the ConCom in its effort to create a film and written history chronicling the evolution of the Lincoln Conservation movement/program. Filming is underway with a priority on capturing oral histories. |
| NR-2.2.1. Provide timely information on the Town’s website, including opportunities for conservation-minded volunteers. |  |  | WC: Info will be on new town website; conservation posted on greeninglincoln.org |
| NR-2.2.2. Provide conservation displays at the library and in the schools. |  |  | WC: Poster and info at Library |
| NR-2.2.3. Continue to work with the schools to provide environmental education to children at all grade levels. |  |  | WC: Conservation taught to 6th grade in 2012 and 2013 |
| NR-2.3.Investigate and seek opportunities to participate in state, national, and global environmental programs, such as dark skies and green cities initiatives. | Low | CC | CC supports this type of initiative. The Green Technology Committee is pursuing some of this and the PB is the group for “dark skies” issues. |
| Goal NR-3. Improve controls against environmental degradation and pollution. |  |  |  |
| RECOMMENDATIONS ACTION STEPS: |  |  |  |
| NR-3.1.Continue to educate the public about alternatives to chemical pesticides, herbicides, and fertilizers in landscaping and lawn maintenance activities. | Ongoing | CC | CC: The Ecological Design and Construction Handbook will convey this type of information. Currently the CC distributes a “Healthy Lawns and Landscapes” brochure and we purchased and distributed the color booklet, “Introduction to Organic Lawns and Yards” published by NOFA. BOH: We do not think we have regulatory or enforcement power to govern the type of plantings and landscaping people use on their lots. Perhaps the planning board or the zoning board could enforce this. We think that public education efforts are the best way to approach this. |
| NR-3. 1.1. Provide public information on the Town’s website and through special displays or exhibits in public buildings. | Ongoing | CC, BOH | CC: Once the new website for the Town is up and running we will be able to populate it with relevant content on this subject. |
| NR-3. 1.2. Implement and enforce Action NR- 1.3.3. |  |  |  |
| NR-3.2.Consider adopting a Low-Impact Development (LID) bylaw, consistent with state stormwater regulations and guidelines, to require developers to include stormwater best management practices (BMPs) in future projects. | Ongoing | WC, CC | CC: The Ecological Design and Construction Handbook will serve much of this need. Where possible we should encourage LID techniques through existing bylaws. If Lincoln needs additional construction bylaws mandated by NPDES then we could incorporate LID language and BMPs into those bylaws. |
| NR-3.2. 1. Evaluate zoning and non-zoning options for a LID bylaw. |  |  |  |
| NR-3.2.2. Evaluate potential confl icts and/or duplication with the town’s subdivision, site plan review, and wetlands protection regulations, and options to regulate land clearing and grading under Recommendation NR-1 .5. |  |  |  |
| NR-3.2.3. Make an objective determination whether a LID bylaw and permitting procedures are necessary to achieve the town’s stormwater management objectives, or if those objectives can be addressed more efficiently and effectively by consolidating stormwater and erosion control permitting with other existing regulations. |  |  |  |
| NR-3.3.Identify and evaluate the town’s options for regulating chemical and sediment pollution of private and public water supplies and establishing local standards for the use of chemical pesticides, herbicides, and fertilizers, to the extent allowed by law. | Low | CC, BOH | CC: Our local Wetlands Protection Bylaw and Surface Water Supply Protection Bylaw, each administered by the CC, do a good job of protecting water quality. The new Groundwater Protection Bylaw is endorsed by the CC and we hope it passes at TM 2013. We will continue to do as much educational outreach in this area as possible. BOH: The Board of Health's agent did not think we have any regulatory or enforcement power over chemical and sediment pollution of private and public water supplies, nor for establishing local standards for use of chemical pesticides, herbicides, and fertilizers. We would defer to town counsel as to whether we have power to promulgate regulations and enforce them. The application of fertilizers is controlled by DEA regulations as to nitrogen loading in proximity to town wells. We think that the water commission should have some say in protection of the Flint's pond, Cambridge reservoir, trapelo road well, and Farrar pond well watersheds. Our agent suggested that we could generate a questionnaire for commercial pesticide and fertilizer applicators (e.g. ChemLawn) to see what controls are imposed by their licensure and whether there is an auditing system to determine whether they meet those controls. |
| NR-3.3. 1. Consult with Town Counsel about local regulatory options. |  |  |  |
| NR-3.4.Adopt noise pollution regulations, with clear standards to define noise disturbance. | Low | PB | PB : Some Board members suggested that NR 3.4, relating to noise control, be given a higher priority (currently low). It would probably require a general bylaw and involve the BOS as well as the Con Com. CC: As a first step toward this goal, the CC is supporting the citizens’ group Quiet Lincoln in its efforts to place reasonable restrictions on the use of leaf blowers in Lincoln. |
| NR-3.4. 1. Define noise pollution and disturbance thresholds, and evaluate regulatory options. |  |  | AC: to be part of this effort because of farm machinery PB: see above |
| NR-3.4.2. Consult with other communities that have adopted noise regulations and review the effectiveness of their bylaws or ordinances and enforcement measures. |  |  | PB: see above |
| NR-3.4.3. Determine appropriate, enforceable regulations for Lincoln and present a bylaw to Town Meeting. |  |  | Ongoing: Land Use Chairs Quarterly |
| NR-3.5.Ensure that new construction projects meet appropriate environmental standards by creating an avenue for reviewing such projects. | Ongoing | PB | PB & CC: Ongoing through site plan review approval criteria and order of conditions |
| NR-3.5. 1. Continue to conduct staff -level development review team meetings to coordinate environmental review and provide consistency in recommendations to town boards. |  | TA |  |
| NR-3 .5.2. Consider opportunities to conduct joint hearings in order to strengthen communication between boards with permitting jurisdiction over new construction projects. |  | PB | Ongoing: Town Offices project was most recent example, when HC and PB conducting a joint hearing. |
| NR-3.6.~ rough identification, public education, regulations, and guidelines, increase the effectiveness of programs to control invasive species and pests. | Ongoing | CC | CC will continue to assume a leadership role on the ongoing issue of invasive species in Lincoln. We work closely with the LLCT and Lincoln Garden Club on this topic. Our annual spring garlic mustard pull effort is a model for surrounding communities. Garden Club, Walden Woods, Mass Audubon MMNHP CISMA SuAsCo; ongoing; Invasives webpage. homeowner packets. Brochures. |
| NR-3.6. 1. Continue to make public information available on the Town’s website. |  |  | CC: Once the new website is functional we will use it for invasive species outreach. |
| NR-3.6.2. Provide information about invasive species and pets available through means such as inserts in mailings from the Water Department. |  |  | CC will consider alternative methods of distribution of educational materials. |
| NR-3.6.3. Provide, maintain, and update public information displays in facilities such as the library, Bemis Hall, and the schools. |  |  | CC will work on educational displays in various locations. Previously the LLCT displayed invasives material in a window at Lincoln Station. |
| Goal NR-4. Improve communication and coordination between the Water Department and other town agencies responsible for developing and implementing natural resource protection plans. |  |  |  |
| RECOMMENDATIONS ACTION STEPS: |  |  |  |
| NR-4.1.Ensure that town agencies have a basic understanding of Lincoln’s drinking water supplies and water storage and distribution systems. | High Ongoing | WC WD | WC: Medium Priority - goals won’t be met this year |
| NR-4.1.1. Encourage consistent communication between staff in the Water Department and other town departments, e.g., through the town’s existing department head meetings and development review team meetings. |  |  | WC: Communication with other departments at Land Use Group meetings |
| NR-4.1.2. Consider providing more information about the town’s water supply and distribution system in the Annual Town Report, including the maximum water withdrawal authorized for Lincoln’s water supplies, comparative consumption trend statistics, and percentage of use attributable to residential, commercial, institutional, and agricultural uses. |  |  | WC – More info in Town Report |
| NR-4.1.3. Prepare a long-range water system master plan and incorporate it within this Comprehensive Plan by amendment. |  |  | WC – Developed 20-yr Capital Plan |
| NR-4.1.4. Fund water system capital improvements in order to reduce unaccounted for water. |  |  | WC – Currently looking into funding opportunities for upgrades |
| NR-4.2.Ensure consistency between Lincoln’s land use policies and water resource protection laws that affect the amount of water Lincoln can withdraw from surface water and groundwater supplies. | Ongoing | WC, CC | WC: Medium priority with focus and, hopefully, completion in 2013; passed Surface Water Protection Bylaw in 2012; Groundwater Protection Bylaw proposed at 2013 TM CC will work with WC to ensure consistency on water withdrawal policy. We support the new Groundwater Protection Bylaw that will come to TM 2013. AC: To be part of this work due to water needs in Ag. |
| NR-4.2.1. Implement Recommendation NR-1.3 and all of its associated action steps. | High | WD, BOS | BOS: See comment on 1.3.1 above. Again, there wouldn’t appear to be a role for the BOS here. |
| NR-4.2.2. Take comprehensive, effective steps to enforce conservation in order to ensure that Lincoln has sufficient water to meet its future growth needs. |  |  |  |
| NR-4.3.Coordinate water conservation efforts among Lincoln’s land use and natural resource agencies and all town departments with operations and maintenance responsibilities for public buildings and grounds. | High | WD, FM | WC: WD - low priority, not this year |
| NR-4.3.1. Implement Recommendation NR-2.1 and all of its associated action steps. |  |  |  |

Notes. (1) Board, committee, and departmental abbreviations: PB, Planning Board; CC, Conservation Commission; CD, Conservation Department; WC, Water Commission; WD, Water Department; FM*, Facilities Manager; BOH, Board of Health; BOS, Board of Selectmen; BOA, Board of Assessors; HOC, Housing Commission; HC, Historical Commission; CPC, Community Preservation Committee; DPW, Department of Public Works; TA, Town Administrator; CCHO*, Council of Cultural and Historic Organizations; SC, School Committee; NCDC*, Neighborhood Conservation District Commission; FC, Finance Committee; FinD, Finance Department; CIPC, Capital Planning Committee; EDC*, Economic Development Committee; TnC, Town Counsel; LC, Library Commission; TC, Town Clerk; IT, Information Technology; LLCT, Lincoln Land Conservation Trust; COA, Council on Aging; FD, Fire Department; PD, Police Department; RC, Recreation Committee; VCC*, Volunteer Coordinating Committee;  AC, Agricultural Commission. (2) Committee names followed by an asterisk (*) are new committees recommended in the Comprehensive Plan.