| HOUSING | CLRP: Priority | CLRP: Lead Board(s) | INFO FROM BOARD: Current Status |
| --- | --- | --- | --- |
| Goal H-1. Provide for a variety of housing types to encourage diversity of Lincoln`s population. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| H-1.1.Create higher-density housing, including a modest amount of additional multi-family housing, in the Lincoln Station area. | High | PB | PB – Gives goal high priority in a sequence of actions with four prior steps corresponding to other goal areas, as follows: - ED 1.1 create a committee – done - ED1.2 review and revise past report – Lincoln Station Planning Committee is starting work - LU 2.1 public planning process – committee has been established, with a charge. Committee will proceed one step at a time, initially examining constraints and potential. Consultant study of Lincoln Woods septic system has been done and provides some useful input. - LU 2.3 capitalize on investment – scope of action will follow from previous stage. - H 1.1 create higher-density housing - BE 4.3 higher-density development in Lincoln Station area linked to open space preservation HOC: In the process of developing a Housing Production Plan, to be ready, hopefully, for 2013 Town Meeting approval. Waiting for consultant’s recommendation regarding the Lincoln Station area, speciofically to advise on whether we need affordable housing there, 80% of median income or above 80% of median income. Whether rental or home ownership. We have not identified any areas suitable for compact housing. |
| H-1.1.1.Through the efforts of the Lincoln Station Planning Committee, identify opportunities for multi-family dwellings and housing in mixed-use developments in the Lincoln Station area. (See also, Goal LU-1.) | High | PB, HOC, LSPC | PB: High priority given to Lincoln Station HOC – see general response to H-1.1 |
| H-1.1.2. Implement the recommendations under Goal LU-1. | High | PB, HOC, LSPC | PB – Response to LU-1 says this can be achieved if a proposal comes in HOC – see general response to H-1.1 |
| H-1.1.3.Determine other areas in Lincoln that may be suitable for compact housing developments similar to Farrar Pond Village or Lincoln Ridge. | High | PB, HOC | HOC – see general response to H-1.1 |
| H-1.2.Consider development incentives such as M.G.L. c. 40R (smart growth) to achieve Lincoln’s housing goals. (See also, LU-3.2.) | Medium | PB |  |
| H-1.2. Consider development incentives such as M.G.L. c. 40R (smart growth) to achieve Lincoln’s housing goals. (See also, LU-3.2.) | Medium | PB |  |
| H-1.3. Encourage retention or creation of smaller homes in order to maintain a range of housing stock available to smaller households and those in early or later stages of life. | High | PB, HOC, HC | HOC: Not feasible – low priority |
| H-1.3.1. Continue to implement and evaluate the effectiveness of Lincoln’s demolition delay bylaw. |  |  |  |
| H-1.3.2. Consider zoning techniques such as allowing construction of small dwelling units on substandard (non-conforming) lots, by special permit. |  |  |  |
| H-1.4.Consider removing zoning obstacles to preserving smaller homes by allowing them to be relocated to another lot with an existing residence for use as an accessory dwelling unit. | Low | PB |  |
| H-1.4.1.Evaluate bylaws and ordinances in other communities (in and outside of Massachusetts) that permit the creation of accessory units through relocation of older homes. |  |  |  |
| H-1.4.2. Study zoning techniques such as Elder Cottage Housing Opportunity (ECHO) bylaws and determine their appropriateness for Lincoln. |  |  |  |
| H-1.5.Encourage accessory apartments to provide more options in current housing stock. | Medium | PB |  |
| H-1.5.1.Allow accessory apartments as of right in single-family dwellings, subject to conditions such as age of the existing dwelling, extent of exterior change allowed to the existing dwelling, maximum unit size, septic system capacity, and screening of off -street parking. |  |  | Pending-subject to recommendations of Housing Production Plan |
| H-1.5.2.Allow accessory apartments by special permit when an applicant’s property does not meet one or more of the conditions for an as-of-right use, e.g., proposals to locate an accessory dwelling in an accessory building on the same lot. |  |  | Ongoing-ZBA special permit process |
| H-1.5.3.Consider providing CPA assistance to homeowners who agree to place an affordable housing restriction on a proposed accessory apartment. |  |  | Pending-subject to recommendations of Housing Production Plan |
| Goal H-2. Provide more housing and/or services to accommodate the needs of individuals who may be under-served by Lincoln`s existing housing stock. |  |  | HOC - question for Housing Plan |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| H-2.1.Determine the need, availability, and cost of in-home services to assist the elderly and people with disabilities so they are able to remain in their own homes if they choose. | Low | HOC | HOC – Not within the scope of the Housing Commission’s Mission |
| H-2.1.1.Work with local and area service providers to identify the home-based service needs of frail elders and people with disabilities. |  |  |  |
| H-2.1.2.Evaluate available models of in-home service delivery and the role(s) of local government in coordinating or providing such services. |  |  |  |
| H-2.1.3.Consider ways to achieve economy of scale by working with other communities on regional solutions to the in-home service needs of seniors and people with disabilities. |  |  |  |
| H-2.2.Conduct outreach and provide information to elderly taxpayers about available programs such as reverse annuity mortgages or work in lieu of property taxes, which might allow them to remain in their own homes for as long as possible. | Ongoing | BOS | BOS: Have developed flyers and other explanatory information and work closely with COA to make seniors aware. Will use the new town web site to better promote the programs. Also BOS is sponsoring a variant for town veterans with similar benefits. |
| H-2.2.1.Continue to provide taxpayer information on the Town’s website. |  |  |  |
| H-2.2.2.Make literature and referrals available through the Council on Aging. |  |  |  |
| H-2.3.Determine the need for additional age-restricted (55+) housing beyond Lincoln’s existing developments, including but not limited to options such as an elderly cottage housing opportunity (ECHO) program. (See also, H-1.4) | Low | HOC | HOC – High Priority for Housing Production Plan |
| H-2.3.1.Survey regional housing market conditions to estimate pipeline of over-55 developments, absorption rates, and vacancies. |  |  |  |
| H-2.3.2.Consult with local and regional service providers on need for additional over-55 housing (independent living units), assisted living, and other types of housing for retirees and the elderly. |  |  |  |
| H-2.3.3.Consider zoning to provide for a variety of housing types and prices for over-55 households. |  |  |  |
| H-2.3.4.Incorporate fi ndings and address with appropriate actions, as warranted, in the Town’s Affordable Housing Plan. |  |  |  |
| H-2.4.Continue to study needs for supportive housing to serve adults with disabilities, particularly adult children of Lincoln residents. | Ongoing | HOC | HOC – High priority. Providing another group home for disabled persons is a goal not yet met |
| H-2.4.1.Consult with local and area service providers about disability housing needs in Lincoln. |  |  |  |
| H-2.4.2.Determine the need for a program for providing basic home repair/maintenance services for people with disabilities who would like to remain in their own homes. |  |  |  |
| H-2.4.3. Determine the need for additional group homes and types of group homes to serve adults with disabilities, particularly adult children of Lincoln residents. |  |  |  |
| H-2.4.4.Maintain a local library of data sources and case studies, such as the WestMetro HOME Consortium’s Five-Year Consolidated Plan. |  |  |  |
| Goal H-3. Maintain Lincoln`s long-standing commitment to provide affordable housing that meets local needs. |  |  | PB: Done- Lincoln's SHI was certified as meeting the local affordable housing need by DHCD upon review of the 2010 Census. Further progress pending subject to recommendations of Housing Production Plan |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| H-3.1.Continue to seek affordable housing opportunities throughout the town, using techniques such as scattered site development, condominium buy-downs, and group homes. | High | HOC, BOS | HOC – High priority BOS – “The BOS supported the efforts of the governing board of Lincoln Woods to reorganize and restructure the financing and governance of LW. We facilitated the acquisition of grant funds that enabled the Lincoln Woods Board to study strategic options to restore financial stability and guarantee Lincoln Woods’ future. We participated actively in discussions with Community Builders and LW residents that culminated in a vote of approval of a reorganization plan. Closing of the transaction and conversion of the units to qualifying rental units (for 40B purposes) is expected in September. Substantial capital improvements will then follow. The Town is currently considering mutually beneficial (to the town and LW) options for municipalization of the LW septic system that would stabilize operation maintenance for the facility and preserve opportunities for the town with regard to serving future commercial development in the Mall area. As noted above, the Housing Troika is monitoring Lincoln’s entire affordable housing stock, and is working to maintain and preserve qualifying units. Currently this involves periodic buy-downs on units at Battle Road Farm which have been funded with roughly equal contributions from the AHT, the Lincoln Foundation and the Commonwealth ($60,000 buy-downs funded with $20,000 each from AHT, LF Massachusetts Department of Housing and Community Development).” The above notes summarize the BOS’ efforts to stabilize Lincoln Woods and to support the Housing Commission and Housing Trust in their efforts. The BOS recently transferred the proceeds from sale of the Twin Pond Lane property to the Housing Trust in furtherance of its mission. |
| H-3.1.1.Evaluate options for the effective use of zoning incentives to encourage creation of affordable housing. | Ongoing | PB, HOC | PB – pending recommendations of the Housing Production Plan HOC – see general response to H-3.1 above |
| H-3.1.2.Continue to commit CPA revenue to affordable housing initiatives conducted or supported by the Lincoln Housing Commission and which are consistent with the Town’s Affordable Housing Plan. | Ongoing | HOC | HOC – see general response to H-3.1 above |
| H-3.1.3.Support efforts to preserve the affordability of Lincoln Woods. | High | HOC, BOS | HOC, BOS – see general responses to H-3.1 above BOS: The town’s short-term interests were largely protected with the sale to Community Builders and the resulting financial stabilization that occurred. The Selectmen/Housing Commission will continue to monitor and to support Lincoln Woods. |
| H-3.2.Ensure that affordable housing is included in residential and mixed-use developments in the Lincoln Station area. | Ongoing | PB, LSPC | PB – pending consultant recommendations from the Lincoln Station Plan underway LSPC – No questionnaire done yet |
| H-3.2.1.As part of the planning process for Lincoln Station (Goal LU-1), explore options for providing affordable units in mixed-use and multi-family developments. |  |  | PB- pending consultant recommendations from the Housing Production Plan and Lincoln Station Plan currently underway |
| H-3.3.Support the Lincoln Housing Commission in setting local targets and strategies to provide affordable housing. | Ongoing | HOC |  |
| H-3.3.1. Provide adequate resources to the Housing Commission to conduct and implement plans and studies to meet local housing needs. |  |  |  |
| Goal H-4. Maintain local control over affordable housing development. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| H-4.1.Review, refine, and update Lincoln’s Affordable Housing Plan. | Ongoing | HOC | HOC – High priority. Study, started in 2011 will be completed in 2013 |
| H-4.1.1.Maintain and implement the town’s Affordable Housing Plan and ensure that the plan meets DHCD requirements for a Housing Production Plan. |  |  |  |
| H-4.1.2.To the extent possible, ensure that Lincoln’s Affordable Housing Plan also meets HUD Consolidated Plan requirements so that Lincoln can continue to participate in the West Metro HOME Consortium and be competitive for state HOME funds. |  |  | HOC - Withdrawing from this program as of 6.30.2013. In process of receiving the full amount of our account to renovate 30 Sunnyside. |
| H-4.1.3. Implement Recommendation H-3.3. |  |  |  |
| H-4.2.Continue to prevent hostile comprehensive permits by ensuring that Lincoln meets the ten percent statutory minimum affordable housing under M.G.L. c. 40B. | High | HOC, BOS | HOC: High priority - plan to meet 10% goal for the next ten year period BOS – “This is a high priority for the Town, but the BOS does not have the primary role. Over the last several years a group (the Housing Troika) consisting of the Housing Commission, the Affordable Housing Trust (AHT) and the Lincoln Foundation has formed and is guiding/coordinating efforts to assure that Lincoln’s subsidized housing inventory (SHI) remains above 10% of its housing stock to meet the requirements of Chapter 40B. This group has secured funding from the CPC for the AHT, which is in a position to move quickly with regard to development of affordable housing. This group is currently pursuing options for additional affordable housing sufficient to meet expected 40B requirements following the 2010 census. It is also working to preserve the affordability of units at Battle Road Farm and Lincoln Woods that are already counted in Lincoln’s SHI.” As the current notes above indicate, the BOS is in a support role here to the Housing Commission and Housing Trust. The Selectmen and Town Administrator are represented on and/or maintain close liaison with the Commission and Trust. |
| H-4.2.1.Commit CPA funds to housing initiatives that produce additional affordable units eligible for the Chapter 40B Subsidized Housing Inventory. |  |  |  |
| H-4.2.2.Monitor market-rate housing development and tailor affordable housing efforts to avoid falling below the ten percent minimum after the next decennial census. |  |  |  |
| H-4.3.Propose, shape, and support positive changes to state legislation that would align with Lincoln’s affordable housing goals without posing a threat to its rural character. | Ongoing | BOS | BOS: Town staff and boards monitor legislation and communicate town’s position to town’s legislators. Most recently, have found ourselves in the position of fending off legislation that would make it more difficult for town to continue to advance its housing objectives – without over-regulation from the state |
| H-4.3.1.Monitor state and federal initiatives levels that could negatively affect Lincoln’s character, upset the balance of existing affordable housing compliance, or usurp local regulation with respect to housing development. |  |  |  |
| H-4.3.2.Oppose initiatives that would impose locally unregulated development on Lincoln’s infrastructure. |  |  |  |

Notes. (1) Board, committee, and departmental abbreviations: PB, Planning Board; CC, Conservation Commission; CD, Conservation Department; WC, Water Commission; WD, Water Department; FM*, Facilities Manager; BOH, Board of Health; BOS, Board of Selectmen; BOA, Board of Assessors; HOC, Housing Commission; HC, Historical Commission; CPC, Community Preservation Committee; DPW, Department of Public Works; TA, Town Administrator; CCHO*, Council of Cultural and Historic Organizations; SC, School Committee; NCDC*, Neighborhood Conservation District Commission; FC, Finance Committee; FinD, Finance Department; CIPC, Capital Planning Committee; EDC*, Economic Development Committee; TnC, Town Counsel; LC, Library Commission; TC, Town Clerk; IT, Information Technology; LLCT, Lincoln Land Conservation Trust; COA, Council on Aging; FD, Fire Department; PD, Police Department; RC, Recreation Committee; VCC*, Volunteer Coordinating Committee. (2) Committee names followed by an asterisk (*) are new committees recommended in the Comprehensive Plan.