| ECONOMIC DEVELOPMENT | CLRP: Priority | CLRP: Lead Board(s) | INFO FROM BOARD: Current Status |
| --- | --- | --- | --- |
| Goal ED-1. Develop the Lincoln Station area as a higher-density mixed-use village that complements and reinforces the vitality of Lincoln’s existing small businesses, consistent with smart- growth principles and Lincoln’s core values. |  |  | PB - Planning Director's Growth Feasibility Analysis completed in October 2011. Town Meeting appropriation of $15,000 for Lincoln Station Planning Consultant services. Ongoing-Lincoln Station Plan nanalysis is underway |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| ED-1.1.Create a Lincoln Station Area Planning Committee appointed by the Planning Board to undertake an initial study of the opportunities, factors and constraints that would inform the necessary steps toward incenting desirable development in the area. | High | PB | PB: Committee created (LSPC) |
| ED-1.2.Review and build upon the Report to the Lincoln Planning Board by the South Lincoln Business Area Planning Committee that was the outcome of the 1998 charrette, and prepare a report that adjusts, refines, or adds to its recommendations to apply to current conditions. | High | PB | PB: Ongoing- LSPC is operational with Lincoln Station Plan |
| ED-1.3.Prepare a needs analysis and feasibility study to determine what commercial activities would best serve the town’s interests. | High | EDC |  |
| ED-1.3.1.Work with the Rural Land Foundation, existing businesses at Lincoln Station, and organizations such as MassDevelopment and the Massachusetts Office of Business Development (MOBD) to fund and carry out a Lincoln Station retail and commercial market study. |  |  |  |
| ED-1.4.Develop realistic economic goals and evaluate the fiscal impact of enacting any recommendations to increase the density of development in the area. | High | EDC |  |
| ED-1.5.Prepare a comprehensive development plan including the infrastructure required to encourage desirable development. |  | BOS? |  |
| ED-1.5.1. Implement Goal LU-1. |  |  |  |
| Goal ED-2. Provide for economic development that respects Lincoln’s rural character and adds to the quality of local residential life by providing goods and services desired by residents, jobs and livelihoods for Lincoln residents, and tax revenue that support the town services that are important to Lincoln residents. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| ED-2.1.Create an Economic Development Committee with members appointed by the Board of Selectmen to identify and assess Lincoln’s economic development opportunities and advise the Board of Selectmen, Planning Board, and other town boards about economic development policy. | Medium | BOS | BOS: Most of the Town’s ED interests and focus has been on South Lincoln. The Selectmen are participating in this Planning Board led effort. Once the South Lincoln planning effort concludes, the Selectmen will meet with the Planning Board to discuss the need for a more town-wide ED focus and the role an ED Committee might play. The BOS also expects to convene a business roundtable in 2013. |
| ED-2.1.1. Establish a nine-member Economic Development Committee appointed by the Board of Selectmen, and prepare a formal committee charge. |  |  |  |
| ED-2.1.2. Conduct outreach to identify residents and business owners interested in serving on the Economic Development Committee. |  |  |  |
| ED-2.1.3. Seek ex officio members for the Economic Development Committee from the Finance Committee, Planning Board, Agricultural Commission, Rural Land Foundation, and the Council for Cultural and Historic Organizations. (See also, CH-1.) |  |  |  |
| ED-2.1.4. Reassess the role, functions, and contributions of the Economic Development Committee within two years of its creation, and determine whether it should be made a permanent town committee. |  |  |  |
| ED-2.2.Consider opportunities for new mixed uses or commercial uses that can be developed and operated for the benefit of the town. | Ongoing | EDC |  |
| ED-2.2.1. Maintain and periodically update information contained in the At-Risk Properties Report (2005). | Ongoing | EDC, BOS | BOS: Action was contemplated to be assigned to the ED Committee (see 2.1 above). In the meantime, the Planning Director and Town Administrator have saved the data in an easily retrievable and searchable format. |
| ED-2.2.2. Working with the Conservation Commission, the Recreation Commission, other boards and private organizations, the Planning Board will lead the effort to determine future land needs and land suitability for various uses, as well as identify areas that may be appropriate for mixed-use or commercial development. |  |  |  |
| ED-2.2.3. Explore and evaluate strategies used in other communities to reuse properties for nonresidential purposes, such as the “Great Estates” zoning that exists in some Berkshire County and Essex County communities. |  |  |  |
| ED-2.2.4. Explore the feasibility of economic development opportunities such as agri-tourism. |  |  |  |
| ED-2.2.5. Establish basic policies and procedures to guide the preparation of development agreements for mixed-use or commercial projects requiring new zoning, drawing upon sources such as the Land Use Review Criteria (Appendix B), the town’s Capital Improvements Plan, and other plans and studies. |  |  |  |
| ED-2.2.6. Ensure that development agreements, when used, are presented to Town Meeting for approval at the same time that Town Meeting is asked to authorize zoning changes, and ensure that approved development agreements are recorded at the Registry of Deeds. |  |  |  |
| Goal ED-3. Retain and capitalize on Lincoln’s cultural, educational, environmental, and other non-profit charitable organizations as a vital part of the local economy. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| ED-3.1.Encourage partnerships between non-profit organizations and local businesses for special events, programs, and other forms of joint marketing that would be mutually beneficial for them and of interest to Lincoln residents. | Medium | EDC, PB | PB: Pending- no EDC is functional at this time. |
| ED-3.1.1. Implement the recommendations under Goal CH-1. ED-3.1.2. Study opportunities for non-profit/for-profit partnerships. |  |  |  |
| ED-3.2.Support non-profit organizations by including their programs and activities on a community-wide calendar maintained on the town’s website. | Medium | EDC, PB | PB: Pending - this responsibility has been assumed by the Website Committee |
| ED-3.2.1. Implement the actions under Recommendation CH-1.2. |  |  |  |
| ED-3.3.Encourage non-profit organizations to provide a variety of educational and enrichment opportunities for Lincoln’s youth, both in and outside of the classroom. |  | BOS? |  |
| ED-3.3.1. Implement the actions under Recommendation CH-1.3. |  |  |  |
| ED-3.3.2. Work with the School Committee to ensure that information about educational and enrichment opportunities is made available to Lincoln students. |  |  |  |
| Goal ED-4. Promote local businesses and home-based businesses as a source of local, "zero-commute" employment. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| ED-4.1.Periodically evaluate the needs of local businesses, such as business services, expansion space, communications technology, networking, or supportive policies from town government. | Low | EDC |  |
| ED-4.1.1. Survey local business owners from time to time, possibly in conjunction with or on the same timetable as need and interest surveys of residents for long-range services and facilities planning (See also, SF-1.1) |  |  |  |
| ED-4.1.2. Identify barriers (if any) to meeting the services and infrastructure needs of local businesses. |  |  |  |
| ED-4.1.3. Determine local government’s responsibility, and evaluate appropriate and realistic options for the Town’s response to business needs. |  |  |  |
| ED-4.2.Review the town’s zoning regulations in order to determine if there are barriers to appropriate at-home employment. |  | BOS? |  |
| ED-4.2.1. Identify residents with home occupations and consult with them to determine whether regulatory barriers exist. |  |  |  |
| ED-4.2.2. T rough formal and informal means, conduct local research to determine whether land use confl icts exist between Lincoln’s variety of home occupations and the surrounding neighborhoods. |  |  |  |
| ED-4.2.3. Review home occupation bylaws and ordinances from other communities similar to Lincoln and determine whether the existing town bylaw should be updated or otherwise modified. |  |  |  |
| ED-4.3.Encourage local businesses to collaborate and coordinate with the town’s non-profit organizations and institutions to address mutual interests, such as planning and cross-promotions of special and seasonal events, and wayfinding to the Lincoln Station area. |  | BOS? |  |
| Goal ED-5. Continue to encourage agriculture as a way of life and a source of local employment and food. |  |  |  |
| RECOMMENDATIONS & ACTION STEPS: |  |  |  |
| ED-5.1.Adopt a right to farm bylaw. |  | AC | AC: Developed a RTF Bylaw in 2011 – see 5.1.4 below |
| ED-5.1.1. Evaluate the state’s model right-to-farm bylaw and similar bylaws adopted in other communities. |  |  |  |
| ED-5.1.2. Consult with agricultural commissions, realtors, developers, lenders, town assessors, and others in communities that have adopted a right-to-farm bylaw and identify advantages and disadvantages (if any). |  | AC | AC: Work performed in 2010 & 2011 |
| ED-5.1.3. Draft a right-to-farm bylaw deemed appropriate for Lincoln and publish it on the Town’s website for public review and comment. |  |  |  |
| ED-5.1.4. Modify the draft based on public input and present to Town Meeting. |  | AC | AC: Presented and adopted at 2011 TM |
| ED-5.2.Support and collaborate with local and regional organizations to promote agri-tourism in Lincoln and increase the base of loyal customers for Lincoln agricultural products. |  | AC | AC: Involvement in MAGIC; creating a Farmer’s Brochure identifying farms in Lincoln & what they sell |
| ED-5.2.1. Consult with the state Department of Agriculture, Department of Conservation and Recreation (DCR), the Metropolitan Area Planning Council (MAPC), the Massachusetts Audubon Society, and other organizations to identify successful agri tourism and community-supported agriculture (CSA) programs in New England. |  |  |  |
| ED-5.2.2. Study successful programs by contacting and visiting them, and determine relevance to Lincoln. |  |  |  |
| ED-5.2.3. Work with Codman Community Farms and other local farms to evaluate the potential benefits and drawbacks of promoting tourism through agriculture. |  |  |  |
| ED-5.2.4. Strengthen and build upon connections between agriculture and local artists and producers of contemporary and traditional craft in order to create new markets for farm and non-farm microbusinesses. |  |  |  |
| ED-5.3.Continue the Conservation Commission’s agricultural leasing program and explore opportunities to expand it, where appropriate. |  | AC | AC: Creating Agricultural maps of current and potential future ag. land |

Notes. (1) Board, committee, and departmental abbreviations: PB, Planning Board; CC, Conservation Commission; CD, Conservation Department; WC, Water Commission; WD, Water Department; FM*, Facilities Manager; BOH, Board of Health; BOS, Board of Selectmen; BOA, Board of Assessors; HOC, Housing Commission; HC, Historical Commission; CPC, Community Preservation Committee; DPW, Department of Public Works; TA, Town Administrator; CCHO*, Council of Cultural and Historic Organizations; SC, School Committee; NCDC*, Neighborhood Conservation District Commission; FC, Finance Committee; FinD, Finance Department; CIPC, Capital Planning Committee; EDC*, Economic Development Committee; TnC, Town Counsel; LC, Library Commission; TC, Town Clerk; IT, Information Technology; LLCT, Lincoln Land Conservation Trust; COA, Council on Aging; FD, Fire Department; PD, Police Department; RC, Recreation Committee; VCC*, Volunteer Coordinating Committee;  AC, Agricultural Commission. (2) Committee names followed by an asterisk (*) are new committees recommended in the Comprehensive Plan.