Construction Period:  April 7, 2014 to April 18, 2014

Daily Right Lane Closures Eastbound and Westbound will be deployed in work zones along Route 2.

Typical Hours for Lane Closures – Eastbound:  9:30 AM – 5:30 PM; Westbound: 7:00 AM – 2:30 PM.

All scheduled work could be extended or delayed due to inclement weather.

- Night Work:

No night Work is scheduled for this two week period.

- Day Work:

Eastbound:

  - Contractor will continue to patch potholes at various locations.

  - Contractor will continue forming and pouring concrete for Retaining Wall #11 located between Sandy Pond Road and Crosby’s Corner

  - Contractor will continue forming, placing reinforcing bars and pouring concrete for East and West Bridge Abutment backwalls located at open area adjacent to Crosby’s Corner.

  - Contractor will begin excavation and forming for wingwall footings at Bridge location in the open area adjacent to Crosby’s Corner.

Westbound:

  - Contractor will continue to install Drainage Pipe at Service Road 2 located between #70 and #74 Cambridge Turnpike.

  - Gas Company will continue installing 12” gas transmission line from #34 Cambridge Turnpike to #46 Cambridge Turnpike

  - Contractor will continue forming and pouring concrete at Wall #20 located in front of #34 Cambridge Turnpike

  - Contractor will continue to patch potholes at various locations.

  - Contractor is processing gravel on site at vicinity of detention basin adjacent to Crosby’s Corner.

  - Contractor will begin installing Roadway gravel at Ramp D vicinity located between #34 Cambridge Turnpike and Crosby’s Corner.

Bedford Road:

  - No work scheduled at this location.

Sandy Pond Road:

  - No work scheduled at this location.